## Sheet1
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | No | Yes | High | Complete | 24 | Yes
Create Google News Scrapper | No | Yes | High | Complete | 8 | Yes
Fetch Busniess news data | No | Yes | High | Complete | 16 | Yes
Convert fetched data into JSON | No | Yes | High | Complete | 0 | Yes
Sprint 2 | No | Yes | Medium | Complete | 96 | Yes
Refine the dataset | No | Yes | Medium | Complete | 32 | Yes
Create a categorization model | No | Yes | High | Complete | 48 | Yes
Run categorization model incoming data | No | Yes | High | Complete | 16 | Yes
Sprint 3 | Yes | Yes | High | Complete | 71 | Yes
Sort dataset based on category | No | Yes | Low | Complete | 5 | Yes
Create a sentiment Analysis Model | No | Yes | Medium | Complete | 56 | Yes
Take weighted mean of scores of each category | No | Yes | Medium | Complete | 10 | Yes
Generate a graph | Yes | Yes | High | Complete | 62 | Yes
Sprint 4 | Yes | Yes | Medium | In Progress | 88 | Yes
Creating UI | Yes | Yes | Low | In Progress | 32 | Yes
Integrating Graph to UI | Yes | Yes | High | Complete | 32 | Yes
Add research data | Yes | Yes | Medium | Complete | 24 | Yes
Sprint 5 | No | No | Low | In Progress | 104 | No
Create a Login function | No | No | Medium | In Progress | 48 | No
Add newsletter function | No | No | Medium | Not Started | 48 | No
Update the Databases | No | No | Medium | In Progress | 8 | No
Create a Product Backlog in Smartsheet

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started